DMAIC Framework

Reducing Avoidable Returns Through Post-Purchase Support Optimization

| Project Duration: | 6 Months | Dataset: | 5,000 Product Returns ¦ Oct 2025 – Sep 2026 |
| --- | --- | --- | --- |
| Scope: | All Product Categories ¦ 5 Regions | Revenue at Risk: | ₹12.68 Cr (Avoidable Returns) |

Executive Snapshot

| Metric | Value | Metric | Value |
| --- | --- | --- | --- |
| Total Returns Analyzed | 5,000 | Returns Prevented (Current) | 328 (14.4% of Avoidable) |
| Avoidable Returns | 2,272 (45.4%) | Average CSAT Score | 2.71 / 5.0 |
| No Support Contacted | 2,717 (54.3%) | Revenue at Risk | ₹12.68 Crore |
| Top Return Reason | Setup/Config Issues (863) | Best Support Channel | Live Chat (20.2% prevention) |

| D | DEFINE — Problem Identification & Project Framing |
| --- | --- |

1.1 Problem Statement

45.4% of all product returns (2,272 out of 5,000) are avoidable, yet 54.3% of customers never contact post-purchase support before initiating a return — resulting in ₹12.68 Crore in preventable revenue loss. Current support interventions prevent only 14.4% of avoidable returns, indicating a significant gap in proactive customer engagement and support accessibility.

1.2 Project Goal

Reduce avoidable product returns by 25% within 6 months through targeted post-purchase support interventions, proactive customer outreach, and multi-channel support optimization.

1.3 Project Scope

| Dimension | In Scope | Out of Scope |
| --- | --- | --- |
| Product Categories | All 10 categories (Laptops, Smartphones, Tablets, Smart Home, Audio, etc.) | Manufacturing defects / supply chain quality |
| Geography | 5 Regions: North, South, East, West, Central | International orders / cross-border returns |
| Return Types | Avoidable returns contactable via support | DOA units, wrong-item deliveries, logistics damage |
| Timeframe | Oct 2025 – Sep 2026 (12-month dataset) | Historical data prior to Oct 2025 |

1.4 Key Stakeholders

| Stakeholder | Role | Interest / Expectation |
| --- | --- | --- |
| PLS Leadership | Executive Sponsor | ROI realization, avoidable return rate reduction |
| Customer Support Team | Operations Owner | Reduced ticket volume, improved resolution scripts |
| Product Teams | Technical SME | Setup guide accuracy, FAQ updates for top issues |
| Brand Partners | External Collaborator | Escalation protocols for compatibility issues |
| Program Manager (Meher) | Project Lead | Program execution, cross-team coordination, reporting |

1.5 SIPOC Diagram

| Suppliers | Inputs | Process | Outputs | Customers |
| --- | --- | --- | --- | --- |
| - Brand Partners - Support Team - Product Catalog - Tech Platform | - Return Request - Customer Query - Product Data - Support Scripts | - 1. Customer contacts support - 2. Issue diagnosed - 3. Resolution offered - 4. Return prevented/processed | - Prevented Return - CSAT Score - Resolved Ticket - Revenue Saved | - End Customer - PLS Leadership - Finance Team |

| M | MEASURE — Baseline Data & Metrics Collection |
| --- | --- |

2.1 Baseline Metrics Dashboard

| KPI | Baseline Value | Target (6 Months) | Status | Business Implication |
| --- | --- | --- | --- | --- |
| Total Returns | 5,000 | — | Reference | Full universe of analysis |
| Avoidable Return Rate | 45.4% (2,272) | ≤34.1% | ⚠ High | Primary improvement lever |
| No Support Contact Rate | 54.3% (2,717) | ≤35% | ⚠ High | Largest opportunity gap |
| Return Prevention Rate | 14.4% (328 returns) | ≥25% | ⚠ Low | Current program effectiveness |
| Average CSAT Score | 2.71 / 5.0 | ≥4.0 / 5.0 | ⚠ Low | Customer satisfaction gap |
| Revenue at Risk | ₹12.68 Crore | ₹9.51 Crore | ⚠ Critical | Financial justification for project |
| Live Chat Prevention Rate | 20.2% | ≥30% | ✓ Best Channel | Model to scale across channels |

2.2 Data Collection Method

Data was extracted from the post-purchase returns management system covering 12 months (Oct 2025 – Sep 2026). Each return record includes purchase metadata, return reason codes, support interaction logs, resolution types, and customer satisfaction scores.

| Data Source | Fields Captured | Volume |
| --- | --- | --- |
| Returns Management System | Order ID, Purchase Date, Return Date, Product Category, Brand | 5,000 records |
| Support Interaction Logs | Support Channel, Interaction Duration, Resolution Type, Return Prevented flag | 2,283 interactions |
| Customer Survey System | CSAT Score (1–5 scale), Post-resolution feedback | 5,000 CSAT scores |
| Product Catalog | Product Price (INR), Category mapping, Brand attributes | 10 categories, 5 regions |

2.3 Returns Classification

Figure 1: 45.4% of all returns were classified as avoidable — preventable with timely support intervention

| A | ANALYZE — Root Cause Investigation |
| --- | --- |

3.1 Pareto Analysis — Return Reason Distribution

The Pareto principle (80/20 rule) was applied to identify the critical few return reasons driving the majority of avoidable returns. The top 3 reasons account for 63.1% of all return volume:

Figure 2: Pareto Analysis — Top 3 return reasons represent 63.1% of total return volume

| Rank | Return Reason | Volume | % of Total | Avoidable? | Root Cause |
| --- | --- | --- | --- | --- | --- |
| #1 | Setup / Config Issues | 863 | 17.3% | ✓ High | Insufficient onboarding guide; customer unable to complete initial setup |
| #2 | Defective / DOA | 648 | 13.0% | Partial | Some DOA cases resolvable via replacement/repair; others are manufacturing issues |
| #3 | Changed Mind | 645 | 12.9% | ✓ High | Post-purchase doubt; no proactive engagement within critical first 72 hours |

3.2 Support Gap Analysis — 54.3% Never Reach Support

Critical Finding: Over half of all returning customers (54.3% — 2,717 out of 5,000) initiated returns without ever contacting support. This represents the single largest preventable loss gap in the program.

| Customer Segment | Count | Returns Prevented | Avg CSAT | Insight |
| --- | --- | --- | --- | --- |
| Contacted Support | 2,283 (45.7%) | 328 (14.4%) | 3.42 / 5 | Higher CSAT; better retention — support engagement clearly helps |
| Never Contacted Support | 2,717 (54.3%) | 0 (0%) | 2.09 / 5 | Zero prevention; lowest satisfaction — proactive outreach could capture this segment |

3.3 Support Channel Effectiveness

Figure 3: Live Chat achieves the highest prevention rate at 20.2% — 1.67x above the lowest channel

| Support Channel | Total Cases | Returns Prevented | Prevention Rate | Avg CSAT | Recommendation |
| --- | --- | --- | --- | --- | --- |
| Live Chat | ∼430 | ∼87 | 20.2% | 3.8 / 5 | ⬆ Scale |
| Phone Call | ∼460 | ∼86 | 18.7% | 3.6 / 5 | ✔ Retain |
| Self-Service Video | ∼390 | ∼64 | 16.4% | 3.4 / 5 | ⬆ Expand |
| Step-by-Step Guide | ∼340 | ∼51 | 14.9% | 3.1 / 5 | ✔ Retain |
| Brand Website | ∼315 | ∼38 | 12.1% | 2.9 / 5 | ▼ Improve |

3.4 Category-Reason Heatmap Insights

Cross-tabulation analysis of product categories against return reasons revealed the following high-priority intervention areas:

| Category | Top Return Reason | Concentration | Actionable Insight |
| --- | --- | --- | --- |
| Laptops | Setup / Config Issues | High | Pre-configured setup calls at delivery; online setup wizard |
| Smartphones | Setup / Config + Changed Mind | High | In-app 'Talk to Expert' within 72 hours of purchase |
| Smart Home Devices | Incompatibility | Medium | Compatibility checker tool + brand partner escalation path |
| Audio Equipment | Performance Issues | Medium | Video troubleshooting guides; peer community forums |
| Tablets | Changed Mind | Medium | Day-3 post-purchase check-in email with tip highlights |

| I | IMPROVE — Targeted Intervention Design |
| --- | --- |

4.1 Five Strategic Interventions

Five evidence-based interventions were designed based on root cause findings, channel effectiveness data, and industry best practices for post-purchase support optimization.

INT-01 ¦ Proactive Push Notifications — Setup Guide Delivery

- Trigger: Automated push notification sent within 24 hours of confirmed delivery - Content: Category-specific setup guide link, top 3 FAQs, direct support CTA - Primary target: Laptops, Smartphones (Setup/Config = #1 return reason — 863 cases) - Expected impact: Reduce setup-related returns by 30-40% within first 7 days

INT-02 ¦ In-App "Talk to Expert" Feature

- Add persistent 'Talk to Expert' Live Chat button on product pages with 10%+ return rate - Trigger availability: Days 1-30 post purchase (highest return risk window) - Rationale: Live Chat has the highest prevention rate at 20.2% — maximize channel utilization - Expected impact: Increase support contact rate from 45.7% to 60%+ within 3 months

INT-03 ¦ Video Troubleshooting Library

- Create 2-5 min video guides for top 5 return reasons per category (25+ videos total) - Host in-app; searchable via product model; available in English, Hindi, and regional languages - Self-Service Video channel currently achieves 16.4% prevention rate — scalable without agent cost - Expected impact: Capture 15-20% of the 2,717 no-contact customers via self-service

INT-04 ¦ Brand Partner Escalation Protocol

- Establish dedicated escalation path to brand partner technical teams for compatibility issues - SLA: Brand responds within 2 hours for Tier-1 products; 24 hours for Tier-2 - Focus: Smart Home (incompatibility #1 reason) — partner-specific troubleshooting wikis - Expected impact: Reduce incompatibility returns by 25% for enrolled brand partners

INT-05 ¦ Post-Purchase Check-In Email Sequence

- Day 3 email: Product highlights, top tip of the week, link to setup video, one-click support access - Day 7 email: CSAT survey + 'Still having trouble? Chat with us' CTA - Personalized: Content tailored by product category; highest-return products get priority - Expected impact: Intercept changed-mind returns (645 cases) before 7-day return window

4.2 Intervention Priority Matrix

| Intervention | Ease of Implementation | Expected Impact | Cost | Timeline | Priority |
| --- | --- | --- | --- | --- | --- |
| INT-01: Push Notifications | High | High | Low | Month 1 | ★★★ P1 |
| INT-02: In-App Talk to Expert | Medium | Very High | Medium | Month 2 | ★★★ P1 |
| INT-03: Video Library | Medium | High | Medium | Month 2-3 | ★★ P2 |
| INT-04: Brand Escalation | Low | Medium | Low | Month 3-4 | ★★ P2 |
| INT-05: Check-In Emails | High | High | Low | Month 1 | ★★★ P1 |

4.3 Projected Impact & Revenue Recovery

Figure 4: Revenue recovery potential at three prevention rate scenarios against ₹12.68 Crore avoidable return pool

| Scenario | Prevention Rate | Returns Prevented | Revenue Saved | Timeline |
| --- | --- | --- | --- | --- |
| Baseline (Current) | 14.4% | 328 | ₹1.83 Cr (implied) | Current State |
| Conservative (Target) | 25% | 568 | ₹3.17 Cr | Month 4-6 |
| Moderate | 40% | 909 | ₹5.07 Cr | Month 8-10 |
| Aggressive | 60% | 1,363 | ₹7.61 Cr | Month 12+ |

| C | CONTROL — Monitoring, Governance & Sustainability |
| --- | --- |

5.1 Power BI Monitoring Dashboard

A Power BI dashboard will serve as the central monitoring tool for the program, accessible to all stakeholders. The dashboard tracks real-time performance against baseline metrics and flags deviations automatically.

| Dashboard Component | Metric Tracked | Visualization Type | Refresh Frequency |
| --- | --- | --- | --- |
| KPI Cards (Top Row) | Avoidable Return Rate, CSAT, Returns Prevented, Revenue Saved | KPI Cards | Daily |
| Trend Line | Weekly avoidable return rate vs. 4-week rolling average | Line Chart | Weekly |
| Channel Performance | Prevention rate by support channel; volume by channel | Bar Chart | Weekly |
| Category Heatmap | Return volume by category and reason; MoM change | Matrix Heatmap | Weekly |
| Intervention Tracker | Status of each INT-01 to INT-05; completion % | Gantt / Table | Weekly |
| Savings Accumulator | Cumulative revenue saved vs. monthly target | Area Chart | Monthly |
| Slicers / Filters | Region, Product Category, Time Period, Support Channel | Dropdown Slicers | Interactive |

5.2 Weekly Review Cadence

| Cadence | Forum | Attendees | Agenda Items |
| --- | --- | --- | --- |
| Weekly (Monday) | Operations Standup | Program Manager, Support Ops Lead | KPI review, alert resolution, channel performance update |
| Bi-Weekly | Cross-functional Sync | PM, Product Teams, Support, Brand Partners | Intervention progress, roadblock escalation, resource needs |
| Monthly | Steering Committee | PLS Leadership, PM, Finance | Financial impact review, trend analysis, strategic adjustments |
| Quarterly | Business Review | Senior Leadership, all stakeholders | DMAIC cycle review, savings report, roadmap for next quarter |

5.3 Alert Triggers & Escalation Protocol

Automated alerts will be configured in Power BI to notify responsible owners when any KPI breaches defined thresholds. The following escalation matrix governs response actions:

| Trigger Condition | Threshold | Alert Level | Notify | Response SLA |
| --- | --- | --- | --- | --- |
| Avoidable return rate increases Week-over-Week | > +5% WoW | ⚠ Critical | PM + Ops Lead | < 24 hours |
| CSAT drops below threshold | < 2.5 / 5 | ⚠ High | PM + Support Lead | < 48 hours |
| Monthly prevention rate below target | < 20% | ⚠ Medium | Steering Committee | < 1 week |
| Channel prevention rate declines | > -3% MoM | ⚠ Low | PM | < 2 weeks |

5.4 Quarterly Program Health Report

At the end of each quarter, Meher (Program Manager) will compile and present a Program Health Report to PLS Leadership covering:

| Report Section | Content | Owner |
| --- | --- | --- |
| KPI Performance vs. Target | Avoidable return rate, prevention rate, CSAT, revenue saved vs. target | Program Manager |
| Intervention Status | Progress on INT-01 to INT-05; completion milestones hit/missed | Program Manager |
| Root Cause Refresh | Updated Pareto analysis; any new return reasons emerging | Data Analyst |
| Financial Summary | Cumulative revenue saved; ROI on interventions deployed | Finance + PM |
| Next Quarter Roadmap | Prioritized actions for Q+1 based on findings; resource requests | Program Manager |

DMAIC PROJECT SUMMARY By implementing the 5 targeted interventions, the PLS program projects: 25% reduction in avoidable returns within 6 months ¦ ₹3.17 Crore in revenue recovered (Conservative) Up to ₹7.61 Crore in annual savings at 60% prevention rate ¦ CSAT target: 4.0 / 5.0 This DMAIC framework demonstrates program management excellence in data-driven decision making, cross-functional stakeholder engagement, and measurable business impact delivery.